## Sheet1
Business Status Report
A Technology Investigation Supporting
Software Architecture and Analysis for Evolution
Cooperative Agreement: F30602-97-2-0031
Quarter ending June 30, 1997
| Received | Expended | Estimate
| to date | through | through
| from RADC1 | 30-JUN-972 | 31-OCT-973
Personnel | 74613 | 25149 | 75000
Fringe Benefits | 9401 | 2978 | 9000
Travel | 11694 | 2615 | 12000
Other | 6074 | 1515 | 6000
Equipment | 4627 | 0 | 5000
Overhead | 47791 | 14125 | 47000
Total | 154200 | 46382 | 154000
1. Column 1 reflects monies received from RADC to
date, and represents the amount RADC has
budgeted for this Agreement through 31-OCT-97.
2. The burn rate will increase as students return in
the Fall of 1997 and resume work on the contract.
3. Projected spending through 31-OCT-97.